## 📊 Dashboard
Agentification Dashboard · Finance
Department progress tracking · Owner: David Carter
% Progress (priority-weighted) |  | % Progress (simple average) |  | 🚧 Blocked processes
|  | 0% |  | 6
Main evaluation KPI |  | every process weighs equally |  | stalled by a dependency
Maturity index (0 = N0 … 4 = N4)
Current maturity | 3
Target maturity | 3
Targets achieved | 1 / 30
Processes with a defined target | 30 / 30
Distribution by CURRENT stage
| N0 | N1 | N2 | N3 | N4
No. of processes | 14 | 3 | 8 | 5 | 0
🚧 Blockers by type (why do they get stuck?)
Data access | 0
Technical dependency | 1
Decision / approval | 0
Budget / resources | 0
Knowledge / key person | 1
Tool / integration | 2
Other | 2
How it is calculated: % Progress per process = (Current stage − Initial) ÷ (Target − Initial); the department % is weighted by the priority SCORE. A process with a Blocker flagged shows as 🔴 Blocked on the Processes sheet, even if it has progress. Everything updates automatically as you fill in the STEP 2 block.

## Processes
AI Agentification Framework — NovaSaaS
Department process sheet · Fill in the white fields · See the "Reference" tab for the scoring scales
Department: |  | Finance |  |  | Owner |  | David Carter |  |  | Date |  | 2026-04-01
STEP 1 · PROCESS IDENTIFICATION | [13 empty] | STEP 2 · TARGET & TRACKING
| E.g. Revenue, CS, Frontend... Leave empty if not applicable | Short, descriptive name | Exploration / Consideration / Decision / Onboarding / Service / Cancellation | Describe the flow: what you do, where you pull data from, who you send it to... | Daily / Weekly / Monthly / When X happens | E.g. 2h each time | HubSpot, Jira, Sheets... | Who does it, how many people | 1-5 | 1-5 | 1-5 | 1-5 | Automatic | Where it started (set once) | Where it is today (update over time) | Committed target | What it takes to get there | When do we consider it optimized? (1 observable sentence) | Automatic | Automatic | Flag the type if it is stalled | What is missing and who does it depend on? | Who drives it | Month / quarter
# | Sub-department (optional) | Process name | Customer Journey stage | Description (what do you do step by step?) | Frequency | Estimated time | Tools / Systems | People involved | Impact (30%) | Manual effort (30%) | Urgency (20%) | Key person (20%) | WEIGHTED SCORE | 🔵 INITIAL stage (N0–N4) | 🟢 CURRENT stage (N0–N4) | 🎯 TARGET stage (N0–N4) | 🔧 Lever | 🏁 Optimization milestone | 📈 % Progress | 🚦 Status | 🚧 Blocker | 📝 Blocker detail | 👤 Owner | 📅 Target date
12 | Accounting close | MRR bridge (HubSpot) vs accounting revenue (Holded) | Internal (not CJ) | Reconcile the MRR reported in HubSpot with the revenue booked in Holded. Identify adjustments, correcting entries and any new entries needed. | Monthly | 4-6h/month | HubSpot, Holded, Excel | Laura, Mark Pierce | 4 | 3 | 4 | 4 | 3.7 | N0 · Manual | N2 · Assisted | N2 · Assisted | Automate |  | 100% | ✅ Achieved |  |  | Laura
7 | A. Receivable | Invoice approval before sending | Service | Before approving the new invoice, it is checked against the same customer's previous invoice to validate amounts, line items and adjustments. Quality control prior to sending. | Monthly | 3-4h/month | Holded, Excel | Laura | 5 | 3 | 4 | 2 | 3.6 | N0 · Manual | N3 · Fully AI | N3 · Fully AI | Automate | The new API is already live; being reviewed to confirm it keeps working | 100% | ✅ Achieved |  |  | Laura
8 | A. Receivable | Sending invoices to customers (ES/EN with #tag) | Service | Send the approved invoices to each customer using the matching template (Spanish or English) and applying the internal tags. | Monthly | 2-3h/month | Holded, Email | Laura | 4 | 3 | 4 | 3 | 3.5 | N0 · Manual | N3 · Fully AI | N3 · Fully AI | Automate | The new API is already live; being reviewed to confirm it keeps working | 100% | ✅ Achieved |  |  | Laura
29 | Controlling | SO Quality Audit | Internal (not CJ) | Automatic quality review of the SOs with a daily Slack message flagging issues. | Daily / Weekly / Monthly / When X happens | <1h/day | HubSpot, Slack | Mark Pierce, David Carter | 4 | 3 | 4 | 3 | 3.5 | N0 · Manual | N3 · Fully AI | N3 · Fully AI | Agentify | It is finished, but the output means people end up not looking at it. Improve the output or set up a process with a clear owner | 100% | ✅ Achieved |  |  | Mark
16 | Accounting close | RAC loan accounting | Internal (not CJ) | Maintain the loan database, book monthly installments and compare against what is paid to the RAC fund. Already underway. | Monthly | 2h/month | Loan Excel, Holded | Laura | 3 | 2 | 4 | 3 | 2.9 | N0 · Manual | N3 · Fully AI | N3 · Fully AI | Automate | It is an app and a skill. A skill to view it graphically in Claude, and an app to view it in a more visual way | 100% | ✅ Achieved |  |  | Laura
14 | Controlling | Analytical billing by product | Internal (not CJ) | Breakdown of monthly billing by product / business line for profitability analysis. | Monthly | 2-3h/month | Holded, Excel, internal engine | Laura | 3 | 2 | 3 | 3 | 2.7 | N0 · Manual | N2 · Assisted | N2 · Assisted | Automate | A skill built inside the finance plugin | 100% | ✅ Achieved |  |  | Laura
32 | A. Payable | Monthly Lumio invoice verification (AUTOMATED) | Internal (not CJ) | Each month Lumio sends a CSV with contracts, rooms, billed days and price. It is already processed by an in-house app (Python/Flask/pandas): it checks line by line, applies per-package caps, generates an Excel with Supplier_Invoice and Internal tabs including MRR, and applies the contractual discount. Status: Done. | Monthly | Before: 4-6h/month · Now: <30min/month | Python app, Excel, HubSpot | Mark Pierce | 3 | 2 | 1 | 2 | 2.1 | N0 · Manual | N2 · Assisted | N2 · Assisted | Automate |  | 100% | ✅ Achieved |  |  | Mark
6 | A. Receivable | Monthly customer billing (HubSpot SOs → Holded) | Service | Generate the monthly customer invoices from the HubSpot Sales Orders and create them in Holded. Directly affects revenue and the end customer. | Monthly | 1 workday/month | HubSpot, Holded | Laura, David | 5 | 4 | 4 | 2 | 3.9 | N0 · Manual | N2 · Assisted | N3 · Fully AI | Agentify | Billing prepared automatically at the press of a button. Human in the loop always to review at the end. The API has changed and is being reviewed so it keeps working | 66.67% | 🔄 In progress |  |  | Laura | Q3
11 | Accounting close | Accruals and close provisions | Internal (not CJ) | Calculation and booking of accruals (deferred income/expenses) and provisions as part of the monthly close. A base engine already exists; the API integration is still pending. | Monthly | 3-4h/month | Holded, Excel, internal engine | Laura | 4 | 3 | 4 | 4 | 3.7 | N0 · Manual | N2 · Assisted | N2 · Assisted | Automate | Income and expenses completed | 100% | ✅ Achieved |  |  | Laura | Q3
15 | Controlling | Actual costs vs Budget comparison | Internal (not CJ) | Compare each month's actuals against the approved budget, producing variances and a suggested commentary | Monthly | 4-6h/month | Holded, Excel, Budget | Mark Pierce | 4 | 3 | 3 | 3 | 3.3 | N0 · Manual | N2 · Assisted | N3 · Fully AI | Mixed | There is a finished skill for the revenue part. The headcount part is also done via a skill. The non-personnel costs part is still missing. To compare properly we need to update and standardize the budget as a new template | 66.67% | 🔴 Blocked | Other | The budget part is still to be finished | Mark | Q3
26 | Accounting close | Variance analysis against budget | Internal (not CJ) | Review and analysis of monthly and annual close variances against budget and forecast | Monthly | 5-6h/month | Excel | Mark Pierce | 4 | 3 | 3 | 3 | 3.3 | N0 · Manual | N2 · Assisted | N3 · Fully AI | Automate | There is a V1 done, still to be polished. Manual trigger, connection to the ERP, produces an Excel output with variances and suggested commentary. Human review | 66.67% | 🔄 In progress |  |  | Mark | Q3
39 | Controlling | Monthly close reports sent to the Board | Internal (not CJ) | After the monthly close, a report is prepared for the Board with the main financial, metric, commercial and other highlights. Until now it was done manually and a summary email was prepared (CFO). | Monthly | 1-2h/month | Excel, Gmail | David Carter | 2 | 4 | 2 | 3 | 2.8 | N0 · Manual | N2 · Assisted | N3 · Fully AI | Mixed | The email draft is prepared automatically based on the close inputs handed to Claude | 66.67% | 🔄 In progress |  |  | David | Q3
35 | Controlling | Metrics preparation and tracking | Internal (not CJ) | Update and analyze the company's monthly metrics. | Monthly | 2-3h/month | Excel, Dashboard built | Mark Pierce, David Carter | 4 | 1 | 1 | 1 | 1.9 | N0 · Manual | N3 · Fully AI | N3 · Fully AI | Agentify | A dashboard capturing the main metrics. Done. | 100% | ✅ Achieved |  |  | Mark | Q3
33 | Controlling | Price-per-Room Analysis (AUTOMATED) | Internal (not CJ) | Recurring price-per-room analysis for customers. Already solved with an in-house tool. | Monthly | Before: 2-3h/month · Now: automated | Excel, internal engine | Mark Pierce | 3 | 2 | 1 | 2 | 2.1 | N0 · Manual | N1 · Digitized | N2 · Assisted | Automate | It is in Beta. Still needs improvement. Report built comparing HubSpot properties to identify margins per hotel and chain, in order to spot patterns and propose improvements. The report exists, but there is bad data in HS that must be corrected for it to be useful (the number of rooms is not always correct) | 50% | 🔴 Blocked | Knowledge / key person | Pending data clean-up by the CX team with Mark. Without it, it is not useful | Mark | Q4
9 | A. Receivable | Debt collection from overdue customers | Cancellation | Review due dates, select unpaid invoices, run steps 2-3 of the debt policy, update the debt Excel and send collection emails. Step 5 (suspension in Atlas) is currently done manually due to a pending dependency. | Weekly | 4-6h/week | Holded, Debt Excel, Email, Atlas | Mark, Customer Support team, AMs, CFO | 5 | 5 | 5 | 4 | 4.8 | N0 · Manual | N0 · Manual | N3 · Fully AI | Agentify | Have an agent that daily identifies due dates in Holded, sends the appropriate reminder emails, notifies the AMs of the account status, and in Atlas sets a banner if needed or suspends the service | 0% | ⬜ Not started |  |  | David | Q3
10 | A. Receivable | Manual service suspension for overdue customers | Cancellation | When a customer reaches step 5 of collection, manually log into Atlas and suspend their access. Blocked by the lack of a technical endpoint. | Monthly (when applicable) | <1h/month | Atlas, Holded | Mark, Customer Support team, AMs, CFO | 5 | 5 | 4 | 2 | 4.2 | N0 · Manual | N0 · Manual | N2 · Assisted | Automate | Have an agent that daily identifies due dates in Holded, sends the appropriate reminder emails, notifies the AMs of the account status, and in Atlas sets a banner if needed or suspends the service | 0% | 🔴 Blocked | Technical dependency | Pending the Tech department enabling the suspension endpoint (Atlas API) | Mark | Q4
38 | Controlling | Cash Flow forecast tracking vs Budget/Forecast | Internal (not CJ) | We have two Excels, one for Budget and one for monthly cash tracking. Currently each week Laura prepares and updates the CF with the inflows and outflows she estimates for the current month, and week by week updates it with the actuals that come in. Every two weeks she meets with Mark to analyze the variances vs Budget/Forecast and then they review it with me. Right now it is a very manual process. We want to improve it so that, as a first step, Budget and Forecast share the same naming. Then it should update automatically and analyze variances. Final step, it should propose improvements | Biweekly | 4-5h/month | Excel and Holded | Laura Bennett, Mark Pierce and David Carter | 3 | 5 | 4 | 4 | 4 | N0 · Manual | N0 · Manual | N2 · Assisted | Mixed | An initial naming comparison between budget and cash forecast that lets us quickly see where the variances are | 0% | 🔴 Blocked | Other | The new budget template is still to be finished | Mark | Q3
1 | A. Payable | Receiving and booking supplier invoices | Internal (not CJ) | We receive supplier invoices through various channels (personal email, Slack, manual download from platforms). They are reviewed, classified and booked one by one in Holded. Covers recurring and new suppliers. | Daily / Weekly | 6-8h/week | Email, Holded | Laura | 4 | 5 | 3 | 2 | 3.7 | N0 · Manual | N0 · Manual | N2 · Assisted | Agentify | An agent ingests data from all invoices daily and books them automatically into the ERP | 0% | ⬜ Not started |  |  | Laura | Q4
37 | Controlling | Budget standardization | Internal (not CJ) | We have a budget template that has been built up over time and is heavily patched. Mark prepares it from my Excel, we review it together, iterate, and present it to the Committee until it is approved. This is done several times a year: an initial budget, and then several forecasts and simulations of additional scenarios as situations arise | Monthly | 2-3h/month | Excel, Holded, HubSpot | Mark Pierce and David Carter | 3 | 4 | 4 | 4 | 3.7 | N0 · Manual | N1 · Digitized | N4 · Fully delegated | Automate | A new Excel template that is lighter, more interpretable and scalable | 25% | 🔄 In progress |  |  | Mark | Q3
17 | Accounting close | Group accounting consolidation | Internal (not CJ) | Consolidate the group entities (Spain, Mexico, etc.) to obtain monthly consolidated accounts. Already underway. | Monthly | 1 workday/month | Holded, Excel | Laura | 2 | 4 | 2 | 4 | 3 | N0 · Manual | N0 · Manual | N2 · Assisted | Automate | Produce a consolidation worksheet combining the parent + subsidiary accounts. It may still need polishing and review, but the first part is done | 0% | ⬜ Not started |  |  | Laura | Q1 2027
18 | Accounting close | Cash management and reconciliation | Internal (not CJ) | Full review and reconciliation of the cash process: bank movements, collections, payments and balances. Pending a full redesign and automation. | Weekly | 2-3h/week | Bank, Holded, Excel | Laura | 3 | 3 | 3 | 3 | 3 | N0 · Manual | N0 · Manual | N2 · Assisted | Automate | Automatic reconciliation of collections and payments from the bank statement against the accounts for all recurring items | 0% | ⬜ Not started |  |  | Laura | Q1 2027
2 | A. Payable | Requesting invoices from the internal team | Internal (not CJ) | Ask each team member to submit expense invoices (reimbursements, one-off purchases) and centralize everything in the A. Payable inbox. Today it is done manually via Slack/email. | Weekly | 1-2h/week | Slack, Email | Laura | 3 | 3 | 4 | 2 | 3 | N0 · Manual | N0 · Manual | N3 · Fully AI | Agentify | The process starts from a single repository and users no longer have to be asked manually to send the invoice. Repository built, notification workflows for users done | 0% | ⬜ Not started |  |  | Laura | Q4
3 | A. Payable | Manual invoice download from external platforms | Internal (not CJ) | Log in monthly to each SaaS platform (Google Workspace, AWS, Anthropic, etc.), download the PDF invoice and forward it to the A. Payable inbox for booking. | Monthly | 2-3h/month | Various SaaS platforms, Email | Laura | 3 | 3 | 4 | 2 | 3 | N0 · Manual | N0 · Manual | N3 · Fully AI | Agentify | An agent that logs into the recurring applications to fetch the invoices and ingest them into the shared repository built for this purpose | 0% | ⬜ Not started |  |  | Laura | Q1 2027
19 | Phase 2 · People | Payroll: Bizneo → Payroll bureau → Holded | Internal (not CJ) | Gather payroll info from Bizneo, prepare a draft email to the payroll bureau, receive the file back and book the employees' payroll in Holded. | Monthly | 3-4h/month | Bizneo, Email, Holded | Laura | 4 | 2 | 2 | 3 | 2.8 | N0 · Manual | N1 · Digitized | N3 · Fully AI | Agentify | The Excel file provided by the payroll bureau connects to Holded and books payroll with an accounting entry. It checks whether there is a new employee and creates them in Holded. Departures must be handled too, still to be defined. Pending linking with Bizneo so it analyzes whether someone is a new hire or a leaver and pulls account number and email data. | 33.33% | 🔄 In progress |  |  | Laura | Q3
5 | Treasury | Payments made vs booked invoices reconciliation | Internal (not CJ) | Match the bank payment movements with the invoices booked in Holded to detect mismatches, duplicates or payments without an invoice. | Monthly | 3-4h/month | Bank, Holded, Excel | Laura | 3 | 2 | 2 | 3 | 2.5 | N0 · Manual | N0 · Manual | N2 · Assisted | Agentify | An agent that pulls data from statements or Holded directly and cross-checks against the accounts to raise error alerts. To be reviewed | 0% | ⬜ Not started |  |  | Laura | Q4
28 | HR | Employee onboarding and offboarding (Bizneo → Payroll bureau → Holded) | Internal (Employee Journey) | An agent gathers onboarding/offboarding info in Bizneo, generates the draft email to the payroll bureau and sends the information. | When it happens | 1-2h each time | Bizneo, Email, Holded | Laura | 3 | 2 | 2 | 3 | 2.5 | N0 · Manual | N0 · Manual | N2 · Assisted | Agentify | An agent that, via a human trigger or automatically through periodic sweeps, captures changes in employee onboarding/offboarding and notifies the payroll bureau by email with a human in the loop | 0% | ⬜ Not started |  |  | Laura / David | Q4
13 | Accounting close | Monthly asset depreciation | Internal (not CJ) | Run the asset depreciation in Holded (the "depreciate" button) on the last day of the month and check that the entries were generated correctly. | Monthly | 2-3h/month | Holded Assets | Laura | 3 | 2 | 2 | 2 | 2.3 | N0 · Manual | N0 · Manual | N3 · Fully AI | Agentify | An agent that, with a human trigger, automatically books the monthly depreciation according to the registered fixed assets and their depreciation rate | 0% | 🔴 Blocked | Tool / integration | It apparently does not pick up the assets via the Holded API | Laura | Q1 2027
4 | A. Payable | Importing Pleo expenses into Holded | Internal (not CJ) | Export the Pleo card expenses and import/book them in Holded monthly. Today it is done manually; the API is still to be investigated. | Monthly | 1-2h/month | Pleo, Holded | Laura | 2 | 2 | 3 | 2 | 2.2 | N0 · Manual | N0 · Manual | N3 · Fully AI | Agentify | An agent extracts data from Pleo and reconciles it with Holded automatically | 0% | ⬜ Not started |  |  | Laura / David | Q1 2027
34 | Controlling | Financial reports requested by investors | Internal (not CJ) | Creating reporting in the format set by investors. The format differs depending on the investor | Monthly | 1-2h/month | Excel, Gmail, internal engine | Mark Pierce | 2 | 3 | 1 | 1 | 1.9 | N0 · Manual | N0 · Manual | N2 · Assisted | Automate | The investor reporting Excel is created automatically based on the given inputs. Manual trigger | 0% | ⬜ Not started |  |  | Mark | Q3
36 | Fixed Assets / Accounting | Intangible fixed asset management | Internal (not CJ) | Register intangible assets in Holded, set up their amortization and book the entry on the last day of the month. | Monthly | 1-2h/month | Holded Assets | Laura | 2 | 1 | 2 | 2 | 1.7 | N0 · Manual | N0 · Manual | N2 · Assisted | Automate | Based on supplier invoices, identify by amount and description what is a fixed asset and book it as such in Holded, registering the asset and its depreciation % according to its nature | 0% | 🔴 Blocked | Tool / integration | It apparently does not pick up the assets via the Holded API | Laura | Q1 2027

## Reference
Reference: Scoring Scales
Use these scales to score each process on the "Processes" sheet. Each criterion runs from 1 to 5.
| IMPACT (Weight: 30%) |  | MANUAL EFFORT (Weight: 30%)
| 1 | Only affects me personally | 1 | Less than 15 minutes a week
| 2 | Affects my work but not others' | 2 | Between 15 minutes and 1 hour a week
| 3 | Affects my team or another department | 3 | Between 1 and 3 hours a week
| 4 | Affects several departments or overall operations | 4 | Between 3 and 8 hours a week (half a day to a full day)
| 5 | Directly affects the end customer or revenue | 5 | More than a full day a week
| URGENCY (Weight: 20%) |  | KEY-PERSON RISK (Weight: 20%)
| 1 | I can live with this indefinitely, no rush | 1 | It is documented and several people have done it before
| 2 | It would be good to improve it, but there is no external pressure | 2 | Several people could do it with some guidance
| 3 | It should be solved this quarter, it is becoming unsustainable | 3 | Only 2-3 people know how to do it and it is not documented
| 4 | There is clear pressure; it will get worse if we don't act soon | 4 | Only 1 person does it, but someone could learn
| 5 | There is a hard deadline or it is blocking me right now | 5 | Only 1 person does it, hard-to-transfer context; if they are away it stops
HOW THE SCORE IS CALCULATED
(Impact × 0.30) + (Effort × 0.30) + (Urgency × 0.20) + (Key person × 0.20) = Weighted score (from 1 to 5)
Example: Impact 5, Effort 3, Urgency 3, Key person 4 → (5×0.30) + (3×0.30) + (3×0.20) + (4×0.20) = 1.5 + 0.9 + 0.6 + 0.8 = 3.8
LEVER / MEANS — what gets you there (NOT a level: it is the type of solution; can be Mixed)
Automate · fixed rules or workflow, no AI
A sequence of steps that is always the same, no decisions. E.g. every Monday move this data from A to B.
Analogy: a bread machine: you give it the recipe and it always comes out the same.
App · a tool that digitizes and structures the process
Takes the work out of paper/email/your head and organizes it in a system. E.g. a form and a dashboard instead of an email.
Analogy: swapping the notebook for a shared sheet that everyone can see.
Agentify · AI that understands, decides and acts
Adapts to the context and executes within rules. E.g. it detects overdue items, drafts and sends the collection notice.
Analogy: a cook you give the rules to, who then decides the day's menu.
AGENTIFICATION STAGES
N0 · Manual | The human does 100% by hand. No system. If the person is away for a week, it stops entirely.
N1 · Digitized | Done in tools with structured data, not on paper or from memory. Still no AI, but traceable.
N2 · Assisted | AI helps with specific steps (drafting, summarizing, classifying). The person reviews and decides each time.
N3 · Fully AI | AI runs the entire flow within rules and acts. The person supervises and only handles the exceptions.
N4 · Fully delegated | Runs on its own, without routine approval. The person defines the policy and reviews the metrics.
Heuristic | Ask yourself: who does the work? and who decides? The higher up the scale, the more the person lets go.
HOW TO MOVE FROM ONE LEVEL TO THE NEXT
N0 → N1 · Digitize: move it out of your head/email/paper into a system with data and statuses. (Lever: App)
N1 → N2 · Copilot: add AI to the most costly steps; the person stays in charge. (Lever: Agentify)
N2 → N3 · Rules and permissions: let the AI run the whole flow and act; the human supervises and sees exceptions. (Lever: Agentify)
N3 → N4 · Remove routine approval: control by exception and audit. Only when the data and the trust allow it.
Note: not every process should reach N4. The right target depends on the risk (an accounting close can healthily cap at N2).
HOW PROGRESS IS MEASURED
% Progress per process = (CURRENT stage − INITIAL) ÷ (TARGET stage − INITIAL).
Example: initial N1, target N3 (a jump of 2). At N2 = 50%. At N3 = 100% (achieved).
Department % = average of the processes WEIGHTED by the priority SCORE. Calculated only on the Dashboard sheet.

## Example
EXAMPLE: Excellence department (real processes)
This is a real example to show you how to fill in your sheet. Don't copy these processes; identify your own.
PROCESS IDENTIFICATION
# | Sub-department (optional) | Process name | Customer Journey stage | Description (what do you do step by step?) | Frequency | Estimated time | Tools / Systems | People involved | Impact (30%) | Manual effort (30%) | Urgency (20%) | Key person (20%) | WEIGHTED SCORE
1 | AI & Ops | Weekly backlog review | Service | Each week I review the 11 Jira backlogs of each department, look for tickets stalled >2 weeks, and write a summary to Michael with alerts. | Weekly | 3-4 hours | Jira, Slack, Google Docs | Alex (only he knows the context) | 5 | 4 | 4 | 5 | 4.5
2 | AI & Ops | Monthly NPS + Product Survey report | Service | I pull data from HubSpot (NPS and Product Survey), calculate deltas vs the previous period, identify detractors, and generate a report for the Tech Board. | Monthly | 2-3 hours | HubSpot, Google Sheets, Docs | Alex + support from Sophie | 4 | 3 | 3 | 4 | 3.5
3 | AI & Ops | Onboarding of new AI tools | Internal (not CJ) | When we adopt a new AI tool, I assess security, create the account, set up permissions, document a usage guide, and train the team. | When X happens | 4-6 hours each time | Claude, Google Workspace, Confluence | Alex | 3 | 3 | 2 | 5 | 3.2